## Sheet1
Project Timeline 9/20 Due 1/24 | Person | 2024-09-20 | 2024-10-04 | 2024-10-25 | 2024-11-08 | 2025-11-29 | 2024-12-06 | 2024-12-20 | 2024-12-27 | 2025-01-10 | 2025-01-16 | 2025-01-24
Create Logo, albums, songs and merch | Gabe
Navbar | Sean
Creating All Pages | Sean & Aidien
Finish Home Page Layout without full design | Sean
Create Sliders to use on all pages | Aidien
Finish Home Page | Sean
Finish About Page | Aidien & Jabari
Finish Tours Page | Aidien & Sean
Finish Albums Page | Aidien
Finish Merch Page | Sean
Create Functioning Shopping Cart | Sean
Finish all merch pages | Sean & Aidien
Making footer | Aidien
Music page | Aidien & Gabe
Individual Merch Pages | Sean & Aidien
Credits | Aidien
Wireframe | Gabe & Jabari
Customer Service Form | Sean & Aidien
Contact Form | Sean
Tour Payment Form | Sean
Testing for Errors and Functionality | Sean, Aidien, Jabari & Gabe
Color Coding
Done + Progress
Working On
Not Started